## Backlog Customer Journeys
Date | 4th June 2018
Team
Aims | Top Level Capture the items for the backlog of Synthetic Data project. NB the matrix is a separate meeting.
ID |  | Title | Description | As a | I want to… | So that… | Notes | Sprint | Status
1 |  | Hardware Requirements | Derermine what hardware requirements are required and source appropriate HW if required. | Data Scientist | be able to run models quickly and effiently | quickly evaluate models |  | 1 | S
2 |  | ID appropriate data sets | ID appropriate datasets to learn/model | Data Scientist | use readily available datasets | I can tran the models |  | 1 | S
3 |  | Imputation | Generate missing parts of data, predict missing values | Data Scientist | generate missing parts of an existing dataset | I can get more complete dataset | May need Cloudera if sensitive data |  | P
4 |  | Back Casting | predict history - baseline archive data that has different measures | ONS Department | baseline archive data | I can provide more useful historical time series comparison |  |  | P
5 |  | Mimic Data | Gnerate whole datasets | Data Sceintist | Generate artifical representative datasets | I can model and analyse data without being concerns about security or privacy of individuals |  |  | P
6 |  | Privacy |  |  | ensure that no one can trace back to a real individual or sensitive datapoint | I can ensure data protection and maintain privacy |  | 1 | S
7 |  | Test Plan |  | Team member | know what I need to test and how | I can efficiently provide evaluation data to the team |  | 1 | S
8 |  | Investigate Algorithms | [5 empty] | 1 | S

## Backlog - Detail
ID | Topic | Task | Depends on | Estimated Duration | Who
1 | Test Plan | Bibliography Review |  | 5 | DP
2 |  | Check with methodology to see if what is being produced is sensible |  |  | DP
3 |  | Test plan outline - Imputation |  |  | DP
|  | Test plan outline - Backcasting | Privacy
|  | Test plan outline - Mimic Data | Privacy
Privacy can delay slightly, but will be required for the end of the test plan and evaluation of models for some applications
4 | Privacy | Review literature on sythentic data privacy-Beaulieu-Jones et al. |  | 0.5
|  | Review literature on sythentic data privacy |  | 0.5
5 |  | Investigate areas of privacy - differential |  | 2
6 |  | Investigate areas of privacy - others US Census B |  | 1
7 |  | Identify core areas of risk |  | 0.5
8 |  | Recommendations for applications |  | 0.5
9 | Investigate Algorithms | AR - background familiarisation |  | 1 | DP
10 |  | AR - create first initial model using Statsmethod/Python |  | 2 | DP
11 |  | AR - train against dataset - Police Data | data set, hw | 4 | DP
12 |  | AR - Evaluate Results for imputation | data set, test plan | 4 | DP | 0 | 0
|  | AR - Evaluate Results for backcastingasting | data set, test plan | 4 | DP
|  | AR - Evaluate Results for Data Mimic | data set, test plan | 4 | DP
13 |  | AR - Optimise Code
14 | Investigate Algorithms | GAN - background familiarisation |  | 5 | IK
15 |  | GAN - create first initial model |  | 7 | IK
16 |  | GAN - train against dataset | data set, hw | 7 | IK
17 |  | GAN - Evaluate Results for imputation | data set, test plan | 4 | IK
|  | GAN - Evaluate Results for backcasting | data set, test plan |  | IK
|  | GAN - Evaluate Results for data mimic | data set, test plan |  | IK
18 |  | GAN - Optimise Code |  | 5 | IK
19 | Investigate Algorithms | AE - background familiarisation |  | 9 | IK
20 |  | AE - create first initial model |  | 9 | IK
21 |  | AE - train against dataset |  | 7 | IK
|  | AE - Evaluate Results for imputation | data set, test plan |  | IK
|  | AE - Evaluate Results for backcasting | data set, test plan |  | IK
22 |  | AE - Evaluate Results for data mimic | data set, test plan | 4 | IK
23 |  | AE - Optimise Code |  |  | IK
24 | Hardware Requirements | Apply for DAP/Cloudera access |  | 0.25 | IK
25 |  | Assess HW needs per model | implemented models |  | IK
|  | GPU Environment for GANs |  | 5
26 | Identify Datasets | Initial selection 3 datasets |  | 2 | IK
27 |  | Upload to DAP if appropriate | order, can take 2 weeks to process | 0.25 | IK
28 |  | Provide details of data location and access
29 | Test Implementation | Build DS test platform | Test Plan, privacy
30 |  | Test each algorithm for accuracy

## Matrix
Model | DataSet | Application | Testing
Auto regression | Police Data
Auto Encoder | Police Data
GAN | Police Data